## README
CTFCU Quantitative Risk Register
Prepared by Giuseppe Scalzo · ISO 27001 Lead Auditor · GRC Capstone Engagement
Purpose | Authoritative record of all identified information security risks at CTFCU. Each risk is scored, owned, treated, and reviewed quarterly.
Framework | ISO/IEC 27001:2022 Clause 6.1 (Risk Treatment), aligned to NIST SP 800-30 and ISO/IEC 27005.
Scoring | Likelihood (1–5) × Impact (1–5). Residual = score after existing controls. Inherent = score with no controls.
Risk Levels | 1–2 Very Low ¦ 3–4 Low ¦ 5–9 Medium ¦ 10–14 High ¦ 15–19 Very High ¦ 20–25 Critical
Sheets in this Workbook
• Risk Register | All 15 identified risks with full scoring, ownership, controls, and treatment
• Treatment Plan | Action plan and cost roll-up for risks above appetite
• Heatmap | Visual 5×5 likelihood-by-impact matrix
Engagement Context | Cumberland Trust Federal Credit Union — $2B regional credit union (TN/KY/AL). Phishing incident Q1 2026 triggered NCUA examination findings and a Board-authorized 18-month GRC program build aligned to NIST CSF 2.0 and ISO 27001:2022.

## Risk Register
Risk ID | Risk Title | Category | Asset(s) Affected | Threat | Vulnerability | Inherent L | Inherent I | Inherent Score | Existing Controls | Residual L | Residual I | Residual Score | Residual Rating | Risk Owner | Treatment Decision | Treatment Action | Annex A Controls | CSF Subcategories
R-01 | Ransomware Attack on Production Systems | Cyber — Avail+Conf | Tier 1 & 2 systems; data warehouse; backups | T-D1 Ransomware; T-I1 Data Exfiltration | Inconsistent patching; MFA gaps on admin; no SIEM | 5 | 5 | 25 | Defender for Endpoint; daily backup; weekly offline copy | 4 | 5 | 20 | Critical | CIO | Mitigate | Deploy SIEM (M8); enforce MFA admin (M5); immutable backups (M6); phishing-resistant MFA (M10) | A.5.7, A.5.23, A.5.24, A.8.7, A.8.8, A.8.13, A.8.16 | PR.AA, PR.DS, PR.IR, DE.CM, RS.CO, RC.RP
R-02 | Insider Threat — Privileged User Abuse | Cyber+Behavioral | Core banking; member master data; HRIS | T-E4 Privilege abuse; T-I6 Insider exfiltration | No JML process; no access reviews; no UEBA | 3 | 5 | 15 | Background checks; basic logging on core systems | 3 | 4 | 12 | High | CIO + HR | Mitigate | PAM platform (M9); quarterly access reviews (M4); UEBA via SIEM (M10); BTAT activation (M3) | A.5.15, A.5.16, A.5.18, A.6.2, A.6.7, A.8.2, A.8.18 | GV.OC, GV.RR, PR.AA, DE.CM
R-03 | Backup Failure During Recovery | Cyber — Availability | Backup repository; recovery capability | T-D1 Ransomware; T-T4 Backup tampering | Backups on prod domain; no offline copy; restore not tested | 2 | 5 | 10 | Daily backup; weekly offline copy | 2 | 5 | 10 | High | IT Ops Mgr | Mitigate | Immutable backup tier (M6); quarterly restore drill (M7); air-gapped Tier 1 (M8) | A.8.13, A.8.14 | PR.DS-11, RC.RP-2
R-04 | Phishing-Driven Credential Compromise | Cyber — Conf+Integrity | Employee identities; M365 tenant; SSO downstream | T-S1 Phishing; T-S4 BEC | Inconsistent MFA on admin; informal training; no simulation | 5 | 4 | 20 | MFA on online banking; M365 spam filter | 5 | 4 | 20 | Critical | InfoSec Mgr | Mitigate | MFA all admin (M5); phishing-resistant MFA pilot (M10); monthly phishing sim (M4); awareness platform (M4); Defender for Office 365 (M4) | A.6.3, A.8.5, A.8.16 | PR.AA, PR.AT, DE.CM
R-05 | GLBA Safeguards Rule Non-Compliance | Compliance | Member NPI; compliance posture | Regulatory action; civil penalties | No formal infosec program; no Qualified Individual | 4 | 4 | 16 | None specific to GLBA Safeguards | 2 | 4 | 8 | Medium | Compliance Officer + CIO | Mitigate | Complete ISMS by M6; GLBA crosswalk M4; designate Qualified Individual M3 | A.5.1, A.5.31, A.5.32, A.5.34 | GV.OC, GV.PO, GV.OV
R-06 | Open NCUA Document of Resolution Items | Regulatory | Regulatory standing | Escalated NCUA enforcement; CAMELS impact | Six open DOR items from May 2026 examination | 5 | 4 | 20 | Active remediation engagement (this program) | 2 | 4 | 8 | Medium | CEO | Mitigate | DOR remediation tracker maintained by Compliance; quarterly reports to NCUA | Cross-cutting | GV.OC-3, GV.OV
R-07 | Critical Third-Party Compromise | Cyber — Conf+Avail | All data dependent on affected vendor | T-I4 Vendor compromise | No formal TPRM; SOC 2 reports not consistently obtained | 4 | 5 | 20 | Contractual review by Legal at onboarding | 4 | 4 | 16 | Very High | CRO | Mitigate+Transfer | TPRM program (M5-M10); SOC 2/ISO 27001 evidence; incident notification SLAs; cyber insurance | A.5.19, A.5.20, A.5.21, A.5.22, A.5.23 | GV.SC, ID.SC
R-08 | Unpatched Critical Vulnerabilities | Cyber — CIA | On-prem servers; workstations; network devices | T-E1 Exploitation of vulnerability | No patch SLAs; CISA KEV items unpatched > 30 days | 4 | 4 | 16 | Quarterly Tenable scans (no remediation tracking) | 3 | 4 | 12 | High | IT Ops Mgr | Mitigate | VM Policy (M4); patch SLAs (14/30/60); monthly KPI reporting; KEV-driven emergency patching | A.8.7, A.8.8, A.8.9 | ID.RA, PR.IP
R-09 | ATM Skimming and Physical Tampering | Physical+Cyber | 38 ATMs; cardholder data | T-P2 ATM attack; T-T5 Physical tampering | No anti-skim hardware on 14 of 38 ATMs | 4 | 3 | 12 | Vendor-managed; surveillance at HQ ATMs only | 3 | 3 | 9 | Medium | ATM Ops Mgr | Mitigate | Anti-skim retrofit (M6-M9); 24/7 monitoring; behavioral analytics from card network | A.7.1, A.7.4, A.7.8 | PR.AA-6, PR.IR-2
R-10 | DDoS Against Online Banking | Cyber — Availability | Online banking; member website | T-D2 DDoS | DDoS protection at provider edge only | 3 | 3 | 9 | Vendor-provided DDoS protection on online banking | 2 | 3 | 6 | Medium | CIO | Mitigate | Verify provider scope (M4); add edge DDoS protection on website (M7); DDoS playbook + tabletop | A.8.6 | PR.IR-3, DE.AE
R-11 | Lost or Stolen Unencrypted Mobile Device | Cyber — Confidentiality | Corporate laptops; corporate mobile phones | T-I2 Lost device | BitLocker not on older laptops; no wipe on 12% mobile | 4 | 2 | 8 | Intune MDM on majority; BitLocker on Win11 | 4 | 2 | 8 | Medium | IT Ops Mgr | Mitigate | 100% BitLocker enforcement via Intune (M5); legacy laptop retirement (M9); 100% Intune mobile (M6) | A.7.9, A.7.10, A.8.1 | PR.DS-3, PR.DS-1
R-12 | Branch Robbery | Physical — Safety | Branch personnel; cash; members in branch | T-P1 Robbery | Inconsistent training; no formal robbery refresher | 3 | 4 | 12 | Cash limits; cameras; alarms; barriers at 8 of 15 branches | 2 | 4 | 8 | Medium | Physical Security Mgr | Mitigate | Annual robbery training (M5); barriers at remaining 7 branches (M12); tabletop with local LE | A.7.1, A.7.2, A.7.3, A.7.4 | PR.AA-6
R-13 | Email Misdirection Disclosing Member NPI | Cyber — Confidentiality | Member NPI | T-I3 Misdirected email | No DLP; no external recipient warning; no encryption | 4 | 3 | 12 | M365 spam filter; informal awareness | 3 | 3 | 9 | Medium | InfoSec Mgr | Mitigate | Purview DLP (M7); external recipient banner (M4); secure portal for member NPI (M8) | A.8.10, A.8.11, A.8.12 | PR.DS-5
R-14 | Pandemic / Regional Disaster — Workforce Unavailability | Operational | Workforce capacity | T-D5 Natural disaster; T-D6 Pandemic | No documented BC plan; no cross-training matrix | 2 | 4 | 8 | M365 remote work; informal cross-training | 2 | 3 | 6 | Medium | COO | Mitigate | Formal BC plan (M8); cross-training matrix; annual pandemic refresh | A.5.29, A.5.30 | RC.RP, ID.BE
R-15 | Workplace Violence Incident at Branch or HQ | Physical+Behavioral | Personnel; physical facility; members on-site | T-P4,P5,P6,P8 Workplace violence variants | No WVP program; no BTAT; no DV intrusion protocol | 2 | 5 | 10 | Branch alarms; informal awareness | 2 | 5 | 10 | High | HR Director + Physical Security Mgr | Mitigate | WVP program (M6); BTAT activation (M3); ALICE/CRASE training (M4-M7); local LE coordination | A.6.3, A.7.1, A.7.2 | GV.RR, PR.AT, PR.IR

## Treatment Plan
Risk Treatment Plan — Action Tracker
Risk ID | Action | Owner | Target Month | Capital Cost | Annual Operating
R-04 | MFA enforced on all admin accounts | InfoSec Mgr | M5 | 0 | 0
R-04 | Security awareness platform (annual) | InfoSec Mgr | M4 | 0 | 40000
R-04 | Monthly phishing simulation | InfoSec Mgr | M4 | 0 | 0
R-04 | Defender for Office 365 (annual) | InfoSec Mgr | M4 | 0 | 24000
R-04 | Phishing-resistant MFA pilot (FIDO2) | InfoSec Mgr | M10 | 18000 | 0
R-01 | Immutable backup tier deployment | IT Ops Mgr | M6 | 65000 | 0
R-01 | SIEM platform deployment | InfoSec Mgr | M8 | 180000 | 90000
R-01 | Quarterly restoration drills | IT Ops Mgr | M7 | 0 | 0
R-07 | Cyber insurance (annual) | CFO | M4 | 0 | 75000
R-07 | TPRM program standup | CRO | M5-M10 | 0 | 0
R-02 | Privileged Access Management platform | IT Ops Mgr | M9 | 120000 | 40000
R-02 | BTAT standup (training+materials) | HR Director | M3 | 15000 | 0
R-03 | Air-gapped backup for Tier 1 | IT Ops Mgr | M8 | 45000 | 0
R-09 | Anti-skimming hardware retrofit | ATM Ops Mgr | M6-M9 | 120000 | 0
R-09 | 24/7 ATM monitoring contract | ATM Ops Mgr | M7 | 0 | 36000
R-11 | Endpoint refresh (legacy laptop retirement) | IT Ops Mgr | M9 | 80000 | 0
R-12 | Annual robbery response training | Phys Sec Mgr | M5 | 0 | 12000
R-12 | Bullet-resistant barriers (7 remaining branches) | Phys Sec Mgr | M12 | 140000 | 0
R-13 | Microsoft Purview DLP (annual) | InfoSec Mgr | M7 | 0 | 48000
R-13 | Secure member NPI delivery portal | InfoSec Mgr | M8 | 0 | 24000
R-15 | ALICE/CRASE training all staff | HR Director | M4-M7 | 28000 | 0
R-10 | Edge DDoS protection on member site | InfoSec Mgr | M7 | 0 | 18000
ISO | ISO 27001 Stage 1 + Stage 2 audit fees | CFO | M16-M18 | 60000 | 0
|  |  | TOTAL | 871000 | 407000

## Heatmap
CTFCU Risk Heatmap — Residual Scores
LIKELIHOOD ↓ | IMPACT →
| 1 · Insignificant | 2 · Minor | 3 · Moderate | 4 · Major | 5 · Severe
5 · Almost Certain |  |  |  |  | R4
4 · Likely |  | R11 |  | R7 | R1
3 · Possible |  |  | R8, R9 | R2, R13
2 · Unlikely |  |  |  | R12 | R3, R15
1 · Rare
Legend: | Very Low (1-2) | Low (3-4) | Medium (5-9) | High (10-14) | Very High (15-19) | Critical (20-25)